## EATERY_ROADMAP
Eatery-Application-RoadMap | 2023 | [12 empty] | 2024 | [11 empty] | 2025
Epic/Feature | Q1 |  |  |  | Q2 |  |  |  |  | Q3 |  |  |  | Q4 |  |  |  | Q5 |  |  |  | Q6 |  |  |  | Q7
Team - 3-PM+11Dev+6QA+2BA+1SCM+4Ux&Ui+2DBA + MVP Build +MOSCOW analysis completed | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 |  | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01
Kickoff meeting | [6 empty] | 2023-07-01: UAT & SIT Testing & Defect Fixing; 2023-09-01: Launch V 1.0 & Defect Fixing; 2024-03-01: UAT & SIT Testing & Defect Fixing; 2024-05-01: Launch V 2.0
Login/Sign up Page User/Supplier/Rider to Login/Signup
User Registration | bar: 2023-10-01 to 2023-12-01; 2024-07-01 to 2024-08-01
Login with OTP
Create Account with Facebook/Twitter/Google
Reset Password
Help Page | bar: 2023-10-01 to 2023-11-01; 2024-07-01
Rider Login
Guest User
Supplier Login | bar: 2023-06-01; 2023-10-01 to 2024-01-01; 2024-06-01
Profile Page User profile and settings page
Edit Personal Details | bar: 2023-10-01 to 2023-12-01; 2024-06-01 to 2024-08-01
Subscription(s) | bar: 2023-11-01 to 2024-01-01; 2024-09-01
Add/edit Address | bar: 2023-10-01 to 2023-11-01; 2024-06-01 to 2024-07-01
Preferences | bar: 2023-11-01 to 2023-12-01; 2024-08-01
Help | bar: 2023-12-01 to 2024-01-01; 2024-08-01 to 2024-09-01
Payment Page User secured payment page
UPI | bar: 2023-10-01 to 2024-01-01; 2024-06-01 to 2024-07-01; 2024-09-01
Net Banking | bar: 2023-10-01; 2023-12-01 to 2024-01-01; 2024-06-01; 2024-08-01 to 2024-09-01
COD | bar: 2023-10-01 to 2023-11-01; 2024-07-01
Add or Edit Credit/Debit Cards | bar: 2023-10-01 to 2023-12-01; 2024-06-01 to 2024-08-01
Saved Cards | bar: 2024-08-01 to 2024-09-01
Digital Wallet | bar: 2024-07-01 to 2024-08-01
App Wallet | bar: 2024-07-01 to 2024-09-01
Sodexo | bar: 2024-09-01 to 2024-10-01
Home Page
Voice Search | bar: 2023-06-01; 2023-12-01 to 2024-02-01; 2024-08-01 to 2024-10-01
Filters | bar: 2023-10-01 to 2024-01-01; 2024-06-01 to 2024-09-01
Sort by Home/hygienic food | bar: 2023-10-01 to 2023-11-01; 2024-06-01
Access menu options | bar: 2023-10-01 to 2023-11-01; 2024-07-01
Search | bar: 2023-10-01 to 2024-01-01; 2024-06-01 to 2024-07-01; 2024-09-01
Food Details | bar: 2023-11-01 to 2024-02-01; 2024-07-01 to 2024-10-01
Ads/Promotions | bar: 2023-06-01; 2023-10-01 to 2024-02-01; 2024-06-01; 2024-08-01 to 2024-10-01
Offers | bar: 2023-10-01 to 2023-11-01; 2024-06-01 to 2024-07-01
Recommendation | bar: 2023-10-01 to 2023-11-01; 2024-01-01; 2024-06-01 to 2024-07-01; 2024-09-01
Tableware | bar: 2023-10-01 to 2024-01-01; 2024-07-01 to 2024-09-01
Party | bar: 2023-12-01 to 2024-01-01; 2024-09-01
Cart Items(Order Page)
Menu item | bar: 2023-11-01 to 2023-12-01; 2024-07-01 to 2024-08-01
Option to Maintain food temperature | bar: 2023-06-01; 2023-12-01 to 2024-02-01; 2024-09-01 to 2024-10-01
Delivery Instructions | bar: 2023-06-01; 2024-01-01 to 2024-02-01; 2024-09-01 to 2024-10-01
Order Quantity | bar: 2023-11-01; 2024-07-01
Change Address to deliver | bar: 2023-12-01 to 2024-01-01; 2024-08-01 to 2024-09-01
Table Ware items | bar: 2023-11-01; 2024-07-01
Menu options | bar: 2023-06-01; 2023-11-01; 2024-01-01 to 2024-02-01; 2024-09-01
Bill Details |  |  |  |  | A/B Testing | bar: 2023-06-01; 2023-10-01 to 2024-02-01; 2024-06-01 to 2024-10-01
Tip for delivery | bar: 2023-06-01; 2023-10-01; 2024-01-01 to 2024-02-01; 2024-06-01; 2024-09-01 to 2024-10-01
Confirm Order | bar: 2023-11-01; 2024-07-01
Apply Coupon | bar: 2023-06-01; 2023-10-01 to 2024-02-01; 2024-06-01 to 2024-08-01; 2024-10-01
Order Tracking Page Tracking user order
Tracking Details | bar: 2023-10-01 to 2024-01-01; 2024-06-01; 2024-08-01 to 2024-09-01
Delivery partner Navigation Map | bar: 2023-11-01 to 2024-01-01; 2024-07-01 to 2024-08-01
Delivery person Contact information
Access Menu | bar: 2023-10-01 to 2023-11-01; 2024-06-01 to 2024-07-01
Delivery Instructions
Order information | bar: 2023-10-01 to 2023-11-01; 2024-06-01 to 2024-07-01
Cancellation | bar: 2023-10-01 to 2023-11-01; 2024-06-01
Customer Support User to connect customer support
FAQ(S) | bar: 2023-10-01; 2024-06-01
Interactive Chat | bar: 2023-11-01 to 2023-12-01; 2024-08-01
Sharing supporting images | bar: 2023-06-01
CALL | bar: 2023-11-01 to 2024-01-01; 2024-07-01; 2024-09-01
Customized Categories | bar: 2023-11-01 to 2023-12-01; 2024-07-01 to 2024-08-01
Refund | bar: 2023-11-01
ABOUT
Feed back & Rating Page
Review | bar: 2023-11-01; 2024-07-01
Feed Back
App Rating | bar: 2024-01-01
Restaurant Rating | bar: 2024-01-01
Rider Rating | bar: 2024-01-01 to 2024-02-01
List of previous Orders | bar: 2023-06-01
Supplier Page | bar: 2023-11-01 to 2023-12-01; 2024-07-01 to 2024-08-01
Menu Items | bar: 2023-10-01 to 2023-11-01; 2024-06-01
Agreement | bar: 2023-11-01; 2024-01-01 to 2024-02-01; 2024-07-01; 2024-09-01 to 2024-10-01
Promotions/Ads to publish | bar: 2023-06-01; 2023-10-01; 2024-06-01
Invoice | bar: 2023-11-01 to 2023-12-01; 2024-07-01 to 2024-08-01
Cutlery & Utensils | bar: 2023-11-01; 2024-01-01 to 2024-02-01; 2024-07-01; 2024-09-01
New Items | bar: 2023-06-01; 2023-12-01
Packaging | bar: 2023-11-01 to 2024-02-01; 2024-07-01; 2024-09-01 to 2024-10-01
Refund & Cancellation Details | bar: 2023-06-01; 2023-11-01 to 2023-12-01; 2024-07-01 to 2024-08-01
Delivery information | bar: 2023-06-01; 2023-12-01 to 2024-01-01; 2024-08-01 to 2024-09-01
Delivery Partner
Order Notification | bar: 2023-10-01 to 2023-11-01; 2024-06-01 to 2024-07-01
Assigning Order | bar: 2023-11-01 to 2024-01-01; 2024-07-01 to 2024-09-01
Reach restaurant | bar: 2023-10-01; 2024-06-01
Call Customer for Order Update | bar: 2023-10-01 to 2023-12-01; 2024-06-01; 2024-08-01
Confirms Order availibility | bar: 2023-06-01; 2023-11-01 to 2024-02-01; 2024-08-01 to 2024-10-01
Delivered | bar: 2023-10-01 to 2023-11-01; 2024-01-01; 2024-06-01 to 2024-07-01; 2024-09-01
Payment per delivery | bar: 2023-06-01; 2023-10-01 to 2024-02-01; 2024-06-01 to 2024-10-01
Bonus reaching 10 deliveries per day | bar: 2023-06-01; 2023-12-01 to 2024-02-01; 2024-08-01 to 2024-10-01
Order picking | bar: 2023-10-01 to 2023-11-01; 2024-06-01 to 2024-07-01
Location details | bar: 2023-06-01; 2023-10-01 to 2024-02-01; 2024-07-01 to 2024-08-01; 2024-10-01
Rewards | bar: 2023-10-01; 2023-12-01; 2024-06-01; 2024-08-01
Tips Received from Customer | bar: 2023-10-01 to 2023-11-01; 2024-01-01; 2024-06-01 to 2024-07-01; 2024-09-01
Customer Review | bar: 2023-06-01; 2023-10-01 to 2024-02-01; 2024-06-01 to 2024-08-01; 2024-10-01
Supplier Review | bar: 2023-06-01; 2023-11-01 to 2024-02-01; 2024-07-01; 2024-09-01 to 2024-10-01
ROADMAP - 2020 | bar: 2023-06-01 to 2023-08-01
| Q1 |  | Q2 |  |  | Q3 | bar: 2023-07-01
Platform - Web / Mobile | bar: 2023-06-01 to 2023-08-01
© Copyright. upGrad Education Pvt. Ltd. All rights reserved
| EPIC / FEATURE |  |  | EPIC / FEATURE |  |  | 2023-11-01: Disclaimer:
All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
|  |  | EPIC / FEATURE |  |  |  | 2023-06-01: EPIC / FEATURE; 2023-11-01: You can download this document from the website for self-use only.
Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
[8 empty] | EPIC / FEATURE |  |  |  | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
|  | Placeholder for Epics / Features added above, Add more details / edit the roadmap as required |  |  |  |  | 2023-11-01: No material in this document will be modified, adapted or altered in any way.
No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
Any rights not expressly granted in these terms are reserved.

## PRODUCT BACKLOG
PRODUCT BACKLOG
S.No | Work Item Type | Work Item Title | Priority (P1, P2 etc) | Comments | Other details, if any
EYPB001 | Functionality | Login Page | P1 | Dev in progress
EYPB002 | Functionality | Create account page | P1 | Dev in progress | QA testing pending
EYPB003 | Functionality | Rider Sign-in Page | P1 | Dev in progress |  | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
EYPB004 | Functionality | Supplier Sign-in Page | P1 | Dev in progress | QA testing pending
EYPB005 | Functionality | Guest User | P1 | Dev in progress | QA testing pending | Disclaimer:
EYPB006 | Functionality | Help Page | P1 | Design is ready |  | All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
EYPB007 | Functionality | Profile Page | P1 | Dev in progress | QA testing pending | You can download this document from the website for self-use only.
EYPB008 | Functionality | Payment Page | P1 | Dev in progress |  | Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
EYPB009 | Functionality | Order tracking Page | P1 | Dev in progress |  | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
EYPB010 | Functionality | Home Page | P1 | Design is ready |  | No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
EYPB011 | Feature | Search | P1 | Design is ready , dev need to create technical spec | Need to review for enhancing the feature | No material in this document will be modified, adapted or altered in any way.
EYPB012 | Functionality | Cart Items(Order Page) | P1 | Design is ready |  | No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
EYPB013 | Feature | Cutlery & Utensils | P1 | Design is ready , dev need to create technical spec | Need to review for enhancing the feature | Any rights not expressly granted in these terms are reserved.
EYPB014 | Functionality | Invoice | P1 | Dev in progress | QA testing pending
EYPB015 | Functionality | Bill Details | P1 | Dev in progress
EYPB016 | Feature | Customer Support | P1 | Design is ready
EYPB017 | Functionality | Feed back | P1 | Design is ready
EYPB018 | Feature | Table Ware | P2 | MVP done
EYPB019 | Feature | Ads/Promotions | P2 | MVP done
EYPB020 | Feature | Food Details | P2 | MVP done
EYPB021 | Functionality | Delivery partner page | P1 | Design is ready
EYPB022 | Feature | Menu item | P1 | Defect fix | QA need to test
EYPB023 | Feature | UPI Integration | P1 | Design is ready
EYPB024 | Feature | Add or edit cards | P1 | Design is ready
EYPB025 | Functionality | Net Banking | P1 | Design is ready,dev to provide technical details
EYPB026 | Feature | Delivery partner navigation map | P2 | MVP done
EYPB027 | Feature | Sign up with Facebook/Twitter/Google | P3 | Design is ready
EYPB028 | Functionality | Reset Password | P1 | Dev in progress | QA testing pending
EYPB029 | Feature | Subscription(s) | P2 | MVP done
EYPB030 | Functionality | Delivery Instructions | P3 | MVP done
EYPB031 | Functionality | Order information | P1 | Dev in progress | QA testing pending
EYPB032 | Feature | Cancellation | P2 | Design is ready,dev to provide technical details
EYPB033 | Feature | Voice Search | P2 | Design is ready,dev to provide technical details
EYPB034 | Functionality | Filters | P1 | Defect fix | QA need to test
EYPB035 | Feature | Apply Coupon | P2 | Dev in progress | QA testing pending
EYPB036 | Feature | Interactive Chat | P3 | MVP done
EYPB037 | Feature | CALL | P3 | MVP done
EYPB038 | Functionality | Review | P1 | Dev in progress | QA testing pending
EYPB039 | Feature | Packaging | P2 | MVP done
EYPB040 | Functionality | Order Notification | P1 | Dev in progress | QA testing pending
EYPB041 | Functionality | Assigning Order | P2 | MVP done
EYPB042 | Functionality | Order picking | P1 | Dev in progress | QA testing pending
EYPB043 | Functionality | Location details | P2 | Design is ready,dev to provide technical details
EYPB044 | Feature | Rewards | P3 | MVP done
EYPB045 | Functionality | Customer Review | P1 | Dev in progress | QA testing pending
EYPB046 | Feature | Offers | P2 | Design is ready,dev to provide technical details
EYPB047 | Functionality | List of previous Orders | P3 | MVP done
EYPB048 | Feature | Option to Maintain food temperature | P1 | Design is ready
EYPB049 | Feature | Recommendation | P2 | Design is ready,dev to provide technical details
EYPB050 | Functionality | Delivery information | P1 | Dev in progress | QA testing pending

## SPRINT BACKLOG
SPRINT BACKLOG - Sprint 1
S.No | Work Item Type | Work Item Title (User Story) | Related Epic / Feature (if any) | Priority (P1, P2 etc) | Status | Comments | Other details, if any
US00001 | Functionaity | As a user I need to tap the application in the device so that I can view the Login page screen | Login Page | P1 | QA to Test | Need to test in IOS & Android
US00002 | Functionaity | As a user I need to login with email successfully so that I can navigate to Home page | Login Page | P1 | Development in progress
US00003 | Functionaity | As a user I need login with mobile number sucessfully so that I can navigate to Home page | Login Page | P1 | Development in progress |  |  | © Copyright. upGrad Education Pvt. Ltd. All rights reserved
US00004 | Functionaity | As a user I need to have guest user option so that I can use the app fo navigate home page and can order the food. | Login Page | P1 | QA to Test | Need to test in IOS & Android
US00005 | Functionaity | As a user/rider/supplier I need to have Forgot password option so that I can reset my password | Login Page | P1 | QA to Test
US00006 | Functionaity | As a supplier I need to have supplier login option so that I can login to app as supplier | Login Page | P2 | Design in progress |  |  | Disclaimer:
US00007 | Functionaity | As a rider I need to have rider login option so that I can login to app as rider | Login Page | P2 | Design in progress |  |  | All content and material on the upGrad website is copyrighted material, either belonging to upGrad or its bonafide contributors and is purely for the dissemination of education. You are permitted to access print and download extracts from this site purely for your own education only and on the following basis:
US00008 | Functionaity | As a user I need to have Create Account option so that I can use the option to create a user account and navigate to signup page. | Login Page | P1 | Development in progress |  |  | You can download this document from the website for self-use only.
US00009 | Functionaity | As a user I need to navigate to Create account page so that I navigate verify number page successfully | Signup Page | P1 | Development in progress
US00010 | Feature | As a user I need to navigate to Verify Number page so that I enter otp and will subcribe the eatery app successfully | Signup Page | P1 | Development in progress | Need to review technicality
US00011 | Functionaity | As a user I create a account successfully so that I can navigate to home page | Signup Page | P1 | Development in progress |  |  | Any copies of this document, in part or full, saved to a disc or to any other storage medium may only be used for subsequent, self-viewing purposes or to print an individual extract or copy for non-commercial personal use only.
US00012 | Functionaity | As a supplier I need to navigate to Create account page and attach agreement so that I can create supplier account and become vendor to the eatery successfully | Signup Page | P2 | Design in progress | Need to review design | Need to approach different stake holder to supply food and get agreements | Any further dissemination, distribution, reproduction, copying of the content of the document herein or the uploading thereof on other websites or use of the content for any other commercial/unauthorised purposes in any way which could infringe the intellectual property rights of upGrad or its contributors, is strictly prohibited.
US00013 | Functionaity | As a rider I need to navigate to Create account page and attach vehicle details and UIDAI details so that I can create rider account and be part of delivery services to the eatery successfully | Signup Page | P2 | Development in progress | Nee to review technical and legal concerns | Need to approach different stake holders for any legal issues. | No graphics, images or photographs from any accompanying text in this document will be used separately for unauthorised purposes.
US00014 | Functionaity | As a user I need to navigate to home page so that I can view the Menu and Search options along with restaurant offerings | Home Page | P1 | Design ready |  |  | No material in this document will be modified, adapted or altered in any way.
US00015 | Functionaity | As a user I need to search select food (Keyword Search) item home page so that I can view the Search results of different restaurant offerings | Home Page | P1 | Development in progress |  |  | No part of this document or upGrad content may be reproduced or stored in any other web site or included in any public or private electronic retrieval system or service without upGrad’s prior written permission.
US00016 | Functionaity | As a user I enter partial search for the food items(Partial Search) in home page so that I can view the suggested partial Search results of different restaurant offerings | Home Page | P2 | Development in progress
US00017 | Feature | As a user I do voice search for the food items(Voice Search) in home page so that I can view the exact voice Search results of different restaurant offerings | Home Page | P3 | Development in progress | Need to review technicality
US00018 | Functionaity | As a user I need to navigate to home page so that I can view the top listed restaurants food items near to me | Home Page | P1 | Design in progress
US00019 | Functionaity | As a user I need to navigate to home page so that I can have filter options to filter different restaurants food items | Home Page | P1 | Design ready
US00020 | Feature | As a user I need to navigate to home page so that I can have filter options to avail cutlery and utensils to my food items | Home Page | P1 | Design ready | Need to review design
SPRINT BACKLOG - Sprint 2 | [7 empty] | Any rights not expressly granted in these terms are reserved.
S.No | Work Item Type | Work Item Title (User Story) | Related Epic / Feature (if any) | Priority (P1, P2 etc) | Status | Comments | Other details, if any
US00021 | Functionaity | As a user I need to have menu option in home page so that I can navigate to menu page and can navigate to different pages to operate | Menu Page | P1 | Need to groom
US00022 | Functionaity | As a user I click on menu option in home page so that I can view the list of functional operation links to navigate in the application | Menu Page | P1 | Need to groom
US00023 | Functionaity | As a user I click on Orders option in Menu page so that I can navigate to my orders page | Menu Page | P1 | Need to groom
US00024 | Functionaity | As a user I click on Payments option in Menu page so that I can navigate to my different Payments option page | Menu Page | P1 | Need to groom
US00025 | Functionaity | As a user I click on H&H option in Menu page so that I can navigate to my different Healthy and hygenic food option page | Menu Page | P1 | Need to groom
US00026 | Functionaity | As a user I click on Cutlery option in Menu page so that I can navigate to my Cutlery and utensils page | Menu Page | P1 | Need to groom
US00027 | Functionaity | As a user I click on Schedule option in Menu page so that I can navigate to my Scheduling page | Menu Page | P1 | Need to groom
US00028 | Functionaity | As a user I click on Offers option in Menu page so that I can navigate to my Offerings page | Menu Page | P1 | Need to groom
US00029 | Functionaity | As a user I click on Profile option in Menu page so that I can navigate to my Profile page | Menu Page | P1 | Need to groom
US00030 | Functionaity | As a user I click on Help option in Menu page so that I can navigate to my Help page | Menu Page | P2 | Need to groom
US00031 | Functionaity | As a user I click on Logout option in Menu page so that I can exist the application succesfully | Menu Page | P1 | Need to groom
US00032 | Functionaity | As a user I click on Restaurant option in Home page so that I can select food items to the cart | Order Page | P1 | Need to groom
US00033 | Functionaity | As a user I click on cart page option without adding any food items so that I can see empty cart page with options to Schedule | Cart Page | P1 | Need to groom
US00034 | Functionaity | As a user I select the food options in Home page so that I can navigate to cart page and can view the list of food items selected | Order Page | P1 | Need to groom
US00035 | Functionaity | As a user I select the proceed to pay option in cart page so that I can navigate to payment page | Cart Page | P1 | Need to groom
US00036 | Functionaity | As a user I can select different payment option so that I can pay my order successfully | Payment page | P1 | Need to groom
US00037 | Functionaity | As a user I pay my order so that I can navigate to delivery tracking page successfully | Payment page | P1 | Need to groom
US00038 | Functionaity | As a user I should view the delivery information clearly so that I can track my order | Delivery tracking page | P1 | Need to groom | Need to configure GPS technicality
US00039 | Functionaity | As a user I should view cancel option in the delivery tracking page for few minutes so that I can still cancel my order | Delivery tracking page | P2 | Need to groom
US00040 | Functionaity | As a user I can view delivery completion so that I can view feedback page to provide the feedback | Delivery tracking page | P2 | Need to groom